## Project Plan
| Special Events | Start | End |  | Project Plan For Steam Heat Controller project
| Time off | 2011-01-29 | 2011-02-11
[5 empty] | 2010-10-01 | [30 empty] | 2010-11-01 | [29 empty] | 2010-12-01 | [30 empty] | 2011-01-01 | [30 empty] | 2011-02-01 | [27 empty] | 2011-03-01 | [30 empty] | 2011-04-01 | [29 empty] | 2011-05-01 | [30 empty] | 2011-06-01 | [29 empty] | 2011-07-01 | [30 empty] | 2011-08-01
 | time axis 2010-10-01 to 2011-08-02
|  | Start | End | % Compl.
Problem Definition |  | 2010-08-30 | 2010-09-07
| Problem Definition Completion | 2010-08-30 | 2010-09-03 | 100%
| End-User(s) and End-Use(s) Identification | 2010-09-02 | 2010-09-07 | 100%
| Constraint Identification | 2010-09-02 | 2010-09-07 | 100%
Technology Considerations and Selection |  | 2010-09-09 | 2010-10-08
| Identification of Possible Technologies | 2010-09-09 | 2010-09-15 | 100%
| Identification of Selection Criteria | 2010-09-15 | 2010-09-21 | 100%
| Technology Research | 2010-09-21 | 2010-09-29 | 100%
| Technology Selection | 2010-09-30 | 2010-10-08 | 100%
End-Product Design |  | 2010-09-24 | 2010-12-31
| Identification of Design Requirements | 2010-09-24 | 2010-10-04 | 100%
| Design Process | 2010-10-04 | 2010-12-31 | 30%
| Documentation of Design | 2010-10-22 | 2010-12-06 | 70%
End-Product Prototype Implementation |  | 2010-11-05 | 2011-02-21
| Implementation of Prototype End Product | 2010-11-19 | 2010-12-16 | 0%
| Identification of Prototype Limitations and Substitutions | 2010-11-05 | 2010-11-18 | 0%
| Identification of Prototype Limitations and Substitutions | 2011-01-01 | 2011-02-14 | 0%
| Implementation of Prototype End Product | 2011-01-01 | 2011-02-21 | 0%
End-Product Testing |  | 2010-12-24 | 2011-04-04
| Test Planning | 2010-12-24 | 2011-01-10 | 0%
| Test Development | 2011-02-15 | 2011-02-21 | 0%
| Test Execution | 2011-02-22 | 2011-03-20 | 0%
| Test Evaluation | 2011-03-20 | 2011-04-02 | 0%
| Documentation of Testing | 2011-03-21 | 2011-04-04 | 0%
End-Product Documentation |  | 2011-01-01 | 2011-04-17
| Development of End-User Documentation | 2011-02-14 | 2011-03-14 | 0%
| Development of Maintenance and Support Documentation | 2011-01-01 | 2011-04-17 | 0%
| Task 3 | 2011-01-28 | 2011-02-03 | 0%
| Task 4 | 2011-01-28 | 2011-02-03 | 0%
End-Product Demonstration |  | 2011-03-01 | 2011-04-11
| Demonstration Planning | 2011-03-01 | 2011-03-14 | 0%
| Faculty Advisor(s) Demonstration | 2011-03-15 | 2011-03-28 | 0%
| Client Demonstration | 2011-03-29 | 2011-04-04 | 0%
| Industrial Review Panel Demonstration | 2011-04-05 | 2011-04-11 | 0%
Project Reporting |  | 2010-08-24 | 2011-05-04
| Project Plan Development | 2010-09-14 | 2010-10-11 | 100%
| Project Poster Development | 2011-03-01 | 2011-04-04 | 0%
| End-Product Design Report Development | 2010-11-22 | 2010-12-07 | 100%
| Project Final Report Development | 2011-04-05 | 2011-05-03 | 0%
| Weekly Email Reporting | 2010-08-24 | 2011-05-04 | 45%
Formulas:
Start = MIN([Start, row below]:D14)
Start = [End, row above]+1
End = [Start]+13
End = MAX([End, row below]:E14)

## Instructions
Project Plan Guide:
•To delete these instructions, select this text box and then hit [Delete].
Date Cells (H6:GU7)
These cells power much of the conditional formatting and allow the project plan to "float." All the cells are indirectly referenced to cell G6, which can be set to a firm date (ex. 2/1/2010) or a reference (ex. =MIN([project dates])). Adjusting cell G6 will shift the entire calendar.
Task Cells (A10:F40)
The tasks have three levels, deliverable, task and sub task. Each has a different conditional format in the Gantt chart area.
Deliverable Sections
The deliverable section(s) (ex. 15:19) can be copied and pasted as rows to add new deliverable sections below the existing sections if needed.
Within each deliverable section you can add additional room for tasks by inserting a row above the light blue row (ex. 13). This way the appropriate conditional formatting is added and no formulas are compromised.
Task s
By entering a task in the B column the conditional formatting will make the associated bar a medium blue. By entering a task in the C column the associated bar will be light blue. The bar is shown via conditional formatting based on the dates entered (Cols D:E) cross referenced with the calendar across the top.
Task dependence/precedence can be managed by creating formulas between the data cells instead of firm dates (ex. =E11+5 vs. 2/10/2010).
Special Events (B2:E7)
Functionality was added to allow for up to five "special events" that will highlight the background color. This was intended for non-task events that may need to be included.
Misc.
- There is a current date indicator that will show the current date on the Gantt chart.
- The Gantt chart bars and the task list will highlight according to % complete status.
- The Page Setup includes repeating rows of 2:9 and repeating columns of A:G. To print a small section of the chart simply select the area of the Gantt chart (ex. H10:AZ41) and set it as the Print Area.
- Hypothetically additional days can be added to the calendar by copy and inserting columns to the left of Column GU. Be sure to check that the formulas in 6:7 and 4:5 have been copied appropriately.

## Version
Version
1 | Initial Version: - Six month view - Floating calendar via conditional formatting - Special events (5) with background fill - Deliverable, task and sub-task levels - Current day indicator
1.1 | Added % complete status for tasks - Added highlighting of Gantt chart bars for % complete - Added highlighting of tasks that are behind plan