## Personnel Effort Requirement
Personnel Effort Requirement (hours)
Personnel Name | Problem Definition | Technology Consideration and Selection | End-Product Design | End-Product Prototype Implementation | End-Product Testing | End-Production Documentation | End-Product Demonstration | Project Reporting | Totals
Cao, Ben | 15 | 60 | 140 | 140 | 190 | 30 | 10 | 15 | 575
Jusufovic, Ben | 20 | 60 | 140 | 140 | 190 | 30 | 10 | 15 | 580
Luong, Thinh | 15 | 60 | 140 | 140 | 190 | 30 | 10 | 15 | 575
Mayberry, Curtis | 20 | 60 | 140 | 140 | 190 | 30 | 10 | 15 | 580
Totals | 70 | 240 | 560 | 560 | 760 | 120 | 40 | 60 | 2310

## Other Required Resources
Other Required Resources
Item |  | Team Hours | Other Hours | Cost
Parts and Materials:
| a) Microcontroller development kit | 0 | 0 | 265
| b) Xbee development kit | 0 | 0 | 50
| c) Controller box | 1200 | 0 | 208.04
| d) Control panel | 1200 | 0 | 115.83
| e) Project poster (printing included) | 12 | 0 | 45
| subtotal | 2412 | 0 | 683.87
Metal Services:
| a) Cutting/welding | 4 | 4 | 0
| b) Mount on steam valve | 1 | 1 | 0
| subtotal | 5 | 5 | 0
Testing and Data Collection
| a) Senior design lab in Coover | 100 | 0 | 0
| subtotal | 100 | 0 | 0
| Totals | 2517 | 5 | 683.87

## Estimated Project Costs
Controller Box
MODULE | ITEM DESCRIPTION | VENDOR | COUNT | PRICE/UNIT | PRICE
DC motor | IG42 24v gear motor | MPJA | 1 | 59.99 | 59.99
Motor driver circuit | L298N | Digikey | 1 | 4.78 | 4.78
Metal platform | Extruded aluminum | 80/20 | 1 | 15 | 15
Tranceiver | Digi Xbee PRO XBee | Digi | 1 | 30 | 30
AC to DC power supply | 120 V 60 Hz to 12 V DC wall converter |  | 1 | 19.99 | 19.99
Miscellaneous components | resistors, capacitors, inductors | ECPE | 1 | 10 | 10
Microcontroller | Atmel AT32UC3A0128 | Mouser | 1 | 10 | 10
Malfunction alarm beeper |  |  | 1 | 1 | 1
LCD and LCD backlight | DOGM128-6 Electronic Assembly | Mouser | 1 | 22 | 22
Ethernet driver | 886-LAN8700C-AEZG | Mouser | 1 | 2.28 | 2.28
PCB |  |  | 1 | 33 | 33
TOTAL |  |  |  |  | 208.04
Control Panel
MODULE | ITEM DESCRIPTION | VENDOR | COUNT | PRICE/UNIT | PRICE
Temperature sensor | IC TEMP-VOLT CONV PREC SOT23B | Digikey | 1 | 0.7 | 0.7
LCD and LCD backlight | DOGM128-6 Electronic Assembly | Mouser | 1 | 22 | 22
Transceiver | Digi Xbee PRO XBee | Digi | 1 | 30 | 30
Miscellaneous components | resistors, capacitors, inductors | ECPE | 1 | 10 | 10
Microcontroller | Atmel AT32UC3A0128 | Mouser | 1 | 10 | 10
Malfunction alarm beeper |  |  | 1 | 1 | 1
Battery | 2 rechargeable NiMH AA batteries |  | 1 | 4 | 4
USB battery recharging circuit | Maxim DS2712E | Mouser | 1 | 5.13 | 5.13
PCB |  |  | 1 | 33 | 33
TOTAL |  |  |  |  | 115.83
Estimated Project Costs
MODULE | ITEM DESCRIPTION | VENDOR | COUNT | PRICE/UNIT | PRICE
Controller panel |  | various | 3 | 115.83 | 347.49
Controller box |  | various | 1 | 208.04 | 208.04
Microcontroller development kit |  | Atmel | 1 | 265 | 265
Xbee development supplies |  | various | 2 | 25 | 50
Subtotal |  |  |  |  | 870.53
LABOR COST |  |  | HOURS | PAY/HOUR | PRICE
Ben Jusufovic | Based on $60000 /year estimate from Career Services |  | 200 | 28.84 | 5768
Ben Cao |  |  | 200 | 28.84 | 5768
Curtis Mayberry |  |  | 200 | 28.84 | 5768
Thinh Luong |  |  | 200 | 28.84 | 5768
Subtotal |  |  |  |  | 23072
TOTAL |  |  |  |  | 23942.53